## Sprint overview
Sprint 1-2 delivery
Sprint | Selected stories | Source effort points | Technical tasks done | Total tasks | Human acceptance
1 | US1-US2 | 8 | 9 | 9 | Not recorded
2 | US3-US5 | 15 | 9 | 9 | Not recorded
Metric | Value
Total source story points | 52
Later story points | 29
Selected story points | 23
Delivered technical scope | US1-US5
Technical delivery and actual Product Owner acceptance are separate.
Source dates are preserved. Course defence dates and real team names were not supplied.

## Sprint tasks
Sprint task tracker
Task ID | Sprint | Story | Task | Owner role | Estimated hours (planning assumption) | Technical state | Evidence
S1-T01 | 1 | Foundation | Set up eight-entity SQLite schema and departments | AI/Backend Developer | 4 | Done | app/schema.sql
S1-T02 | 1 | Foundation | Implement registration, hashed passwords, session rotation and CSRF | AI/Backend Developer | 6 | Done | app/server.py; app/security.py
S1-T03 | 1 | US1 | Prepare labeled training and separate evaluation data | AI/Backend Developer | 4 | Done | data/training.json; data/evaluation.json
S1-T04 | 1 | US1 | Implement supervised classifier, confidence and safety guards | AI/Backend Developer | 5 | Done | app/ml.py
S1-T05 | 1 | US1 | Implement request CRUD and automatic department routing | AI/Backend Developer | 5 | Done | app/service.py
S1-T06 | 1 | US2 | Persist receipts and notification history with unique event links | Frontend Developer | 4 | Done | app/service.py; app/schema.sql
S1-T07 | 1 | US1-US2 | Build student intake and notification interface | Frontend Developer | 6 | Done | static/app.js; static/style.css
S1-T08 | 1 | US1-US2 | Verify routing, notices, validation and privacy | QA Tester | 4 | Done | tests/test_acceptance.py
S1-T09 | 1 | Management | Prepare proposal, backlog, architecture and report | Product Owner / Scrum Master | 3 | Done | docs/sprint_1/report.md
S2-T01 | 2 | US3 | Persist admin-adjustable threshold | AI/Backend Developer | 3 | Done | app/server.py; app/schema.sql
S2-T02 | 2 | US3 | Implement four-business-hour review deadline and overdue flag | AI/Backend Developer | 3 | Done | app/database.py; app/service.py
S2-T03 | 2 | US3 | Record staff corrections with original request snapshot | AI/Backend Developer | 3 | Done | app/service.py
S2-T04 | 2 | US4 | Implement support authorization, sorting and queue filters | AI/Backend Developer | 4 | Done | app/server.py
S2-T05 | 2 | US4 | Build direct routing and reassignment UI | Frontend Developer / UX Designer | 5 | Done | static/app.js
S2-T06 | 2 | US5 | Implement state transitions, resolution, history and versions | Full-stack Developer | 5 | Done | app/service.py
S2-T07 | 2 | US5 | Implement student list polling while preserving form inputs | Full-stack Developer | 3 | Done | static/app.js
S2-T08 | 2 | US3-US5 | Verify 500 requests, ownership, rerouting and concurrency | QA Tester | 5 | Done | tests/test_acceptance.py
S2-T09 | 2 | Management | Prepare criteria audit, sprint report, evidence and delivery ZIP | Product Owner / Scrum Master | 4 | Done | docs/criteria_audit.md; docs/sprint_2/report.md
Hours are planning assumptions, not measured time. Replace role owners with actual team names.

## Product backlog
Product backlog
#story | story_title | story description | story_estimation | HC&HV | LC&HV | HC&LV | LC&LV | User_role | Pre-Requirements | QATest | Responsible person in a team | Source Iteration | Source Deadline | Course Sprint | Delivery state
1 | AI Student Request Classification & Routing | As a student, I want my questions and requests to be automatically sent to the right school department, so that I get help quickly without having to figure out who to ask. | 5 |  | yes |  |  | Student | Student must be logged into the student portal; support departments/categories must be set up in the system | US1QATest | AI/Backend Developer & QA Tester | 1 | 2026-11-15 | 1 | Implemented
2 | Routing Confirmation & Student Notification | As a student, I want to receive a notification confirming which department received my request, so that I know my request is being handled and who to expect a response from. | 3 |  | yes |  |  | Student | AI routing engine (Story 1) is implemented; notification service (email/in-app) is configured | US2QATest | Frontend Developer | 1 | 2026-11-30 | 1 | Implemented
3 | Low-Confidence Escalation to Staff | As a student, I want my request to be reviewed by a staff member when the AI is unsure how to classify it, so that my request still gets routed correctly instead of being lost or mishandled. | 5 | yes |  |  |  | Student / Support Staff | AI routing engine (Story 1) is implemented; confidence threshold is configured; staff review queue exists | US3QATest | AI/Backend Developer | 2 | 2026-12-15 | 2 | Implemented
4 | Staff Manual Routing Dashboard | As a support staff member, I want a dashboard that shows all escalated and unassigned student requests, so that I can quickly review and route them to the correct department. | 6 | yes |  |  |  | Support Staff | Staff member must have a 'support' role account; escalation flow (Story 3) is implemented | US4QATest | Frontend Developer & UX Designer | 2 | 2026-12-22 | 2 | Implemented
5 | Request Status Tracking | As a student, I want to check the status of a request I submitted (Received, In Progress, or Resolved), so that I know what is happening with it without contacting the department directly. | 4 |  | yes |  |  | Student | AI routing engine (Story 1) is implemented; request status field is defined in the data model | US5QATest | Full-stack Developer | 2 | 2026-12-29 | 2 | Implemented
6 | Priority / Urgent Request Detection | As a student submitting an urgent issue (e.g., a health or safety emergency), I want the system to automatically detect the urgency and immediately alert the right department, so that critical issues are handled without delay. | 7 | yes |  |  |  | Student / Health Services | AI classification model (Story 1) is implemented; a real-time alert channel (SMS/email/push) is available | US6QATest | AI/Backend Developer | 3 | 2027-01-15 | 3 | Backlog
7 | Multi-language Request Handling | As a student who prefers to write in Kazakh or Russian, I want to submit my request in my own language and have it classified and routed correctly, so that I don't struggle to describe my issue in English. | 5 |  | yes |  |  | Student | AI classification model (Story 1) is implemented; a language-detection library is available | US7QATest | AI/Backend Developer & Localization Specialist | 3 | 2027-01-22 | 4 | Backlog
8 | Student Feedback on Resolution | As a student whose request has been resolved, I want to rate the support I received and leave optional comments, so that the school can measure and improve support quality. | 3 |  |  |  | yes | Student | Request status tracking (Story 5) is implemented; a request can be marked Resolved by staff | US8QATest | Frontend Developer | 3 | 2027-01-29 | 5 | Backlog
9 | Admin Analytics Dashboard | As a school administrator, I want a dashboard showing request volume, AI routing accuracy, and department response times, so that I can monitor support-system performance and staffing needs. | 6 |  |  | yes |  | School Administrator | Request, feedback (Story 8), and staff-correction (Story 3) data is being logged | US9QATest | Data Analyst & Backend Developer | 4 | 2027-02-10 | 5 | Backlog
10 | AI Model Retraining Pipeline | As an IT administrator, I want the AI classification model to be periodically retrained using new labeled data, so that routing accuracy keeps improving instead of degrading over time. | 8 | yes |  |  |  | IT Administrator | Feedback (Story 8) and staff-correction (Story 3) data is available; ML training infrastructure is provisioned | US10QATest | AI/ML Engineer | 4 | 2027-02-20 | 6 | Backlog
Source: supplied AI_Student_Routing_10_User_Stories (3).xlsx, main sheet rows 3-12. Original workbook preserved in docs/source/.
Course Sprint and Delivery state are explicit adaptations. Source Iteration, deadlines, roles, estimates and priority flags are retained.

## Burndown plan
Burndown plan and build snapshot
Working day | Sprint 1 ideal points | Sprint 1 observed points | Sprint 2 ideal points | Sprint 2 observed points
0 | 8 |  | 15
1 | 7.2 |  | 13.5
2 | 6.4 |  | 12
3 | 5.6 |  | 10.5
4 | 4.8 |  | 9
5 | 4 |  | 7.5
6 | 3.2 |  | 6
7 | 2.4 |  | 4.5
8 | 1.6 |  | 3
9 | 0.8 |  | 1.5
10 | 0 |  | 0
Snapshot | Sprint 1 remaining | Record | Sprint 2 remaining | Record
Current build | 0 | Technical implementation | 0 | Technical implementation
Ideal values are a plan. Daily observed values are blank because historical daily records were not supplied.
The build snapshot records implementation, not actual team acceptance or velocity.